## Defects
Page Name | Defect | Technical | Style | Status | Next Steps | Due Date
Home | INK small logo | When you scroll down the homepage the smaller ink nav logo doesn't link. Is this intentional? | Is this correct? Should the small INK logo on the homepage take the user back to the top of the page? | Corrected & Tested | None | 2017-01-09
| JP Morgan Chase & Co. logo link | Link news to open new window |  | In Progress | Simran to assure links opens to a new window | 2017-01-09
| You Should Know links to You Should Know main page |  | Should You Should Know link to landing page or content page? | In Progress | Myles to send Simran updated styling for page landing page for Simran to address. | 2017-01-09
|  | How to recognize and avoid phishing' image doesn't link (and probably should be anchor link) |  | In Progress | Story to be replaced on the homepage by 1/9. Myles to extract copy and redesign cyber smarts. | Phase 2 (redesign of cyber smarts)
|  | Underlining issues with titles and authors; underlining, however, not linking. |  | Corrected & Tested |  | 2017-01-09
| Each story has an title, author (no author for 15 mins with) and picture when opened and content is correct (content) |  | Should we have a subheader, similar to the print version? Also are we using image captions? Not right now, up to business | in Progress | Myles to send Simran subheader styling, implemented by 1/9. Image captions will be determined by the business when they do UAT. | 2017-01-09
| Navigation | Navigation on mobile pushes News |  | Corrected & Tested |  | 2017-01-09
|  | all pages top nav is too wide in IE 11 and forcing horizontal scroll bar |  | Corrected & Tested |  | 2017-01-09
On Location | Field reports opens to multiple pictures and summaries (4) | Date has underline on hover. |  | Corrected & Fixed
In Pictures | Title #2 links to gallery of 6 pictures | page has 5 pics, not 6 |  | Corrected & Tested
You Should Know |  | can't scroll down in chrome on You Should Know page |  | In Progress | Simran to address | 2017-01-09
Ask INK |  | Clicking 'ASK?INK' above title directs to http://ink-dev.jpmchase.net/templates/news.html |  | Corrected & Tested |  | 2017-01-09
|  |  | Need style guide for ASK INK logo | In Progress | Myles to send Simran updated styling | 2017-01-09
Footer |  | In IE 11, blue footer bar not full width of page on ASK INK page |  | Corrected & Tested |  | 2017-01-09
|  | Special character is present Â© in ASK INK |  | Corrected & Tested |  | 2017-01-09
Content | News stories (global)
|  | Replace hyphens with em dashes in all News Stories, where appropriate (see example on next tab) |  | In Progress | Simran to continue to correct all stories | 2017-01-09
| Features | Women in the Move - It says “Byline” it does not have an author or maybe byline just needs to be removed since it is only images |  | Corrected & Tested |  | 2017-01-09
| On Location | In Switzerland - Switzerland is spelled wrong This does not have subhead either: Subhead: A look at the firm’s Switzerland business as leaders descend on Davos this month. |  | Corrected & Tested |  | 2017-01-09
| You Should Know | On the main: http://ink-dev.jpmchase.net/templates/You-should-know.html it shows the Good Apps subhead twice |  | Corrected & Tested |  | 2017-01-09
| Alignment | Put rule on the bottom of the copy to have lines align |  | In Progress | Simran to address the spacing rule | 2017-01-09
| Print & Email icons | Should they be so far apart |  | In Progress | Simran to bring them closer together and to hotlink | 2017-01-09

## Hyphen vs em dash example
Hyphens were used here:
They should be converted to em dashes like in the word doc: